## 测出问题
问题点1
回答：
已修改
问题点2 |  |  |  | 未解决
解决方案
后台推送一个websocket的消息给前端，消息体【{"buyId":"11","buyUserId":"2","type":"buyCoinConfirm"}】
前端在websocket的onmessage的监听中，对返回的消息体进行解析，如果type是buyCoinConfirm的时候做什么事情，如果是chat的时候做什么事情
|  |  |  | 后端推送的几种消息体 |  | 根据type进行操作
聊天
{"chatFromUserId":"11","chatToUserId":"1","content":"你好呀","avatar":"xxxx","type":"chat"}
买家下单
{"from":"0","type":"buyCoinStart","content":"买家下单","bussineType":"buyCoin","bussineId":26}
卖家已确认
{"from":"10","type":"buyCoinConfirm","content":"卖家已确认售卖","bussineType":"buyCoin","bussineId":28}
买家已付款
{"from":"11","type":"buyCoinPayed","content":"买家已付款","bussineType":"buyCoin","bussineId":23}
卖家已确认收款
{"from":"10","type":"buyCoinFinish","content":"卖家已确认收款，订单完成","bussineType":"buyCoin","bussineId":23}
商户取消
{"from":"10","type":"buyCoinMerchantUserCancel","content":"商户取消","bussineType":"buyCoin","bussineId":26}
买家取消
{"from":"11","type":"buyCoinBuyUserCancel","content":"买家取消","bussineType":"buyCoin","bussineId":28}
卖家取消
{"from":"10","type":"buyCoinSaleUserCancel","content":"卖家取消","bussineType":"buyCoin","bussineId":31}
订单超时，自动取消
{"from":"0","type":"buyCoinAutoCancel","content":"订单超时，自动取消","bussineType":"buyCoin","bussineId":26}
订单确认超时，自动完成
{"from":"0","type":"buyCoinAutoFinish","content":"订单确认超时，自动完成","bussineType":"buyCoin","bussineId":32}
问题点3
回答：
在后台的【系统管理 -> 支付审核】这个页面里，进行审核
问题点4 |  |  | 未解决
回答：
同问题点2一起修改，前端接受服务器消息推送，进行弹窗提醒
问题点5 | [6 empty] | 未解决
回答
原因买单已超时，但是页面没刷新还是提交了撤销，导致撤销2次，数据重复
解决方法
同问题点2一起修改，前端接受服务器消息推送,如果撤单发生，则弹窗提醒
并且服务器撤销时判断状态，避免重复撤单
问题点6 |  | 未解决
回答
同问题5一起解决了。重复撤单的缘故
问题点7
回答：
未解决
第一张图，前端需要修改
第二张图回答内容
卖家扣币是在挂单的时候就已经扣了，买家买的时候不需要重复扣币
问题点8
回答：
增加了一个【买币驳回】的按钮，把这笔买卖取消
问题8
未解决
更新微信收款码的时候，会带有支付宝的图片信息。
更新支付宝收款码的时候，会带微信图片的信息。
前端改成当前更新哪个，就只传哪个的值